## Instructions
Menu | Instructions
AI Audit Workbook
Purpose | Operational workbook for tracking AI inventory, control testing, maturity scoring, findings, remediation planning, and certification readiness.
How to Use | 1. Start by listing all known AI systems in the AI Inventory tab. 2. Use Control Testing to document control design and operating effectiveness. 3. Score each audit domain in Maturity Scoring. 4. Record issues in Findings Register. 5. Track remediation in the 30-60-90 Plan. 6. Summarize readiness gaps in Certification Readiness.
Suggested Workflow | Inventory -> Control Testing -> Maturity Scoring -> Findings Register -> 30-60-90 Plan -> Certification Readiness-> Summary Dashboard
Scoring Guidance | Use a 1-5 maturity scale unless otherwise defined. Score based on evidence, consistency, ownership, and monitoring.
Status Definitions | Open= Not started , In Progress=Currently being worked, Completed=finished, Deferred=intentionally postponed, not cancelled, and should be revisited later. It is still relevant, but work will occur later due to dependencies, resourcing, timing, or leadership decision. Ready / Not Ready / Partial
Maturity Guidance | Managed = strong, consistent, and well-documented Defined = mostly established with some remaining gaps Developing = foundational elements exist but need formalization Initial = early stage with significant gaps
Version | 1
Owner | Rubin Fletcher
Project | AI Audit Checklist & Certification Playbook

## AI Inventory
System Name | Business Unit | Owner | AI Type | Purpose | Data Sensitivity | Risk Level | Data Type | Human Oversight Required | Vendor / Platform | Status | Last Review Date | Notes
Internal HR Assistant | Human Resources | HR Systems Manager | Generative AI | Draft HR guidance and answer internal policy questions | High | High | Employee Data | Yes | Microsoft Azure OpenAI | Active | 2026-04-20 | Responses should be reviewed before employee guidance is issued.
Customer Support Copilot | Customer Service | Support Operations Lead | Generative AI | Assist agents with response drafting and customer support workflows | Moderate | Medium | Customer Account Data | Yes | Salesforce + LLM Integration | Under Review | 2026-04-20 | Human review is required before final customer communication.
Resume Screening Model | Talent Acquisition | Recruiting Manager | Predictive AI | Rank applicants for recruiter review and prioritization | High | High | Applicant Data | Yes | Third-Party HR Vendor | Active | 2026-04-20 | Output should support, not replace, recruiter hiring decisions.
Security Alert Triage Assistant | Security Operations | SOC Manager | Generative AI | Summarize and prioritize security alerts for analyst review | Moderate | Medium | Security Log Data | Yes | Internal App + Model API | Active | 2026-04-20 | Analysts should validate prioritization before response action.
Marketing Content Generator | Marketing | Marketing Director | Generative AI | Draft campaign content and internal marketing material | Low | Low | Public / Internal Business Data | Yes | Third-Party SaaS AI Tool | Active | 2026-04-20 | Use should be limited to approved business content and brand review.

## Control Testing
Control ID | Control Domain | Control Objective | Control Description | Owner | Test Method | Evidence Reviewed | Design Effectiveness | Operating Effectiveness | Result | Notes | Remediation Needed
GOV-01 | Governance | Ensure each AI system has clear accountability | Each AI system should have a defined business or technical owner with documented oversight responsibility | AI Program Lead | Review AI Inventory and ownership assignments | AI Inventory, governance records | Effective | Effective | Pass | Ownership is documented for systems currently in scope | No
RISK-01 | Risk Management | Ensure AI systems are risk rated consistently | Each AI use case should be assigned a risk level using defined and repeatable criteria | Risk Manager | Review risk scoring entries for consistency | AI Inventory, risk methodology notes | Effective | Needs Improvement | Partial Pass | Risk levels exist, but criteria should be standardized further | Yes
DATA-01 | Data Governance | Ensure data used by AI is identified and classified | Data sources, sensitivity, and approved use should be documented for each AI system | Data Owner | Review inventory fields and supporting documentation | AI Inventory, data classification references | Effective | Needs Improvement | Partial Pass | Data sensitivity is tracked, but source approval and lineage may need stronger support | Yes
HIL-01 | Human Oversight | Ensure human review is defined where needed | Higher-risk AI systems should require documented human review before final action | Compliance Lead | Review oversight requirements for high-risk systems | AI Inventory, process notes | Needs Improvement | Needs Improvement | Fail | Human oversight exists in practice, but documentation and consistency need improvement | Yes
SEC-01 | Security | Ensure access to AI systems is controlled | Access to AI systems and connected data should be restricted to authorized users | Security Lead | Review access control approach and approval process | Access review records, system access notes | Effective | Effective | Pass | Access control expectations appear defined for active systems | No
MON-01 | Monitoring | Ensure AI systems are reviewed after deployment | AI systems should be periodically reviewed for misuse, drift, errors, or business impact | Operations Lead | Review monitoring and review cadence documentation | Review logs, monitoring notes, dashboards | Needs Improvement | Needs Improvement | Partial Pass | Monitoring activity may exist, but it is not yet formalized across the program | Yes

## Maturity Scoring
Domain | Score | Max Score | Percentage | Maturity Level | Notes
Governance | 4 | 5 | 80% | Managed | Ownership and accountability are defined for in-scope systems, but oversight documentation can still improve.
Risk Management | 3 | 5 | 60% | Defined | Risk levels are assigned, but criteria need stronger standardization.
Data Governance | 3 | 5 | 60% | Defined | Data sensitivity is tracked, but lineage, source approval, and usage constraints need stronger documentation.
Human Oversight | 2 | 5 | 40% | Developing | Human review exists for some use cases, but requirements are not consistently formalized for higher-risk systems.
Security | 4 | 5 | 80% | Managed | Access expectations appear strong, though recurring review evidence should improve.
Monitoring | 2 | 5 | 40% | Developing | Monitoring is recognized as important, but review cadence and formal procedures remain limited.
Overall Program Maturity | 18 | 30 | 60% | Defined | Overall program has a solid foundation, but human oversight and monitoring need stronger formalization before higher readiness can be claimed.

## Findings Register
Finding ID | Audit Area | Issue Summary | Risk Level | Impact | Recommendation | Owner | Target Date | Status | Evidence Reference
F-001 | Risk Management | AI risk ratings are documented, but scoring criteria are not fully standardized across systems | Medium | Inconsistent ratings may lead to uneven review and approval decisions | Define and document standard AI risk rating criteria, then revalidate current entries | Risk Manager | 2026-05-20 | Open | RISK-01
F-002 | Data Governance | Data sensitivity is tracked, but source approval and lineage are not fully documented | High | Weak data traceability may increase compliance and governance risk | Document approved data sources, lineage, and usage constraints for each in-scope AI system | Data Owner | 2026-05-25 | Open | DATA-01
F-003 | Human Oversight | Human review requirements for higher-risk AI systems are not consistently documented | High | Decisions may rely too heavily on AI outputs without documented oversight | Define formal human oversight requirements and approval points for high-risk systems | Compliance Lead | 2026-05-22 | In Progress | HIL-01
F-004 | Monitoring | AI monitoring and periodic review activities are not formalized across the program | Medium | Drift, misuse, or performance issues may go undetected or be inconsistently handled | Create a documented monitoring procedure with review cadence and ownership | Operations Lead | 2026-05-30 | Open | MON-01
F-005 | Security | Access expectations appear defined, but recurring evidence of periodic access review is limited | Low | Excess or outdated access may remain in place longer than intended | Establish a recurring access review log with signoff and retention requirements | Security Lead | 2026-06-05 | Open | SEC-01

## 30-60-90 Plan
Timeframe | Action Item | Objective | Owner | Priority | Status | Notes
30 Days | Standardize AI risk scoring criteria | Make AI risk ratings more consistent and repeatable across systems | Risk Manager | High | Open | Supports closure of the risk management finding and improves certification readiness.
30 Days | Define formal human oversight requirements | Document when human review is required for higher-risk AI systems | Compliance Lead | High | In Progress | Highest-priority gap because oversight is not yet consistently formalized.
60 Days | Document approved data sources and lineage | Improve traceability for data used by AI systems | Data Owner | High | Open | Needed to strengthen data governance and evidence quality.
60 Days | Establish recurring access review evidence process | Improve proof of periodic access review and signoff | Security Lead | Medium | Open | Security controls are strong, but evidence retention should improve.
90 Days | Create formal AI monitoring procedure | Define review cadence for drift, misuse, output quality, and performance | Operations Lead | High | Open | Supports monitoring maturity and certification readiness.
90 Days | Reassess certification readiness and update dashboard | Confirm remediation progress and refresh readiness status | AI Program Lead | High | Open | Final review step after major remediation items are updated.

## Certification Readiness
Requirement Area | Status | Evidence Available | Gaps Identified | Owner | Target Completion Date | Notes
Governance Structure | Ready | Yes | Minor documentation improvements remain | AI Program Lead | 2026-05-15 | Ownership and accountability are largely defined for in-scope systems.
Risk Assessment Process | In Progress | Yes | Risk scoring criteria need stronger standardization | Risk Manager | 2026-05-20 | Risk levels exist, but methodology needs to be more repeatable.
Data Governance Controls | In Progress | Partial | Data lineage, source approval, and usage constraints need stronger documentation | Data Owner | 2026-05-25 | Data classification is present, but documentation depth needs improvement.
Human Oversight Controls | Not Ready | Partial | Formal review requirements are not consistently documented for higher-risk systems | Compliance Lead | 2026-05-22 | Human oversight exists in practice, but policy and workflow requirements need formalization.
Security Controls | Ready | Yes | Recurring access review evidence should improve | Security Lead | 2026-06-05 | Access expectations appear strong, though evidence collection should mature.
Monitoring and Review | In Progress | Partial | Monitoring cadence and review procedures are not formalized across the program | Operations Lead | 2026-05-30 | Monitoring activities exist, but they are not yet consistent or well documented.

## Summary Dashboard
AI Audit Certification Playbook Dashboard
Metric | Value | Finding Status
Total AI Systems | 5 | Open | 4
Open Findings | 4 | In Progress | 1
In Progress Findings | 1 | Closed | 0
Closed Findings | 0
Overall Program Maturity | Defined
Certification Ready Areas | 2
Certification Areas In Progress | 3
Certification Areas Not Ready | 1
Open Action Items | 5
Dashboard Interpretation | Table Summary
Category
Program Maturity Status | Program is mostly established but still has some gaps.
Findings Status | Several open findings require attention.
Certification Readiness Status | One certification area is not ready.